ID Task Name

# 0 KAANAPALI ROYAL - SLOPED ROOF REPLACEMENT

1 **CONSTRUCTION WORK**

2 **General Conditions**

# 9 PHASE 1 DEMO - BLDGS A - E

10 BUILDING A

11 BUILDING B

12 BUILDING C

13 BUILDING D

14 BUILDING E

# 15 PHASE 1 TILE INSTALL - BLDGS A - E

16 BUILDING A

17 BUILDING B

18 BUILDING C

19 BUILDING D

20 BUILDING E

# 21 PHASE 2 - BLDGS F - Q, OFFICE

22 BUILDING F

23 BUILDING G

24 BUILDING H

25 BUILDING J

26 BUILDING K

27 OFFICE BUILDING

28 BUILDING L

29 BUILDING M

30 BUILDING N

31 BUILDING P

32 BUILDING Q

# 33 PHASE 2 - CLEAN UP AND DEMOB

34 Substantial completion date

35 Clean-up & Demobilize

36

37 GREEN: TASK/BUILDING COMPLETED

38 YELLOW: TASK/BUILDING IN PROGRESS

39 BLUE: TENTATIVE SCHEDULE

Duration

**257 days**

**257 days**

**62 days**

**26 days**

7 days

6 days

6 days

6 days

6 days

**41 days**

9 days

10 days

10 days

10 days

10 days

**127 days**

14 days

14 days

14 days

14 days

14 days

6 days

14 days

14 days

14 days

14 days

14 days

**196 days**

0 days

1 day

0 days

0 days

0 days

Start

**Mon 6/17/24 Mon 6/17/24 Mon 6/17/24 Mon 9/9/24** Mon 9/9/24 Mon 9/16/24 Mon 9/23/24 Mon 9/30/24 Mon 10/7/24 **Fri 10/11/24** Fri 10/11/24 Tue 10/22/24 Fri 11/1/24 Wed 11/13/24 Mon 11/25/24 **Mon 1/6/25** Mon 1/6/25 Fri 1/24/25 Tue 2/11/25 Fri 2/28/25 Tue 3/18/25 Fri 4/4/25

Thu 4/10/25 Tue 4/29/25 Thu 5/15/25 Tue 6/3/25 Fri 6/20/25 **Mon 9/16/24** Thu 7/10/25 Fri 7/11/25

Mon 9/16/24 Mon 9/16/24 Mon 9/16/24

Finish

**Fri 7/11/25 Fri 7/11/25 Mon 9/16/24 Mon 10/14/24** Tue 9/17/24 Mon 9/23/24 Mon 9/30/24 Mon 10/7/24 Mon 10/14/24 **Tue 12/10/24** Wed 10/23/24 Mon 11/4/24 Thu 11/14/24 Tue 11/26/24 Tue 12/10/24 **Thu 7/10/25** Fri 1/24/25 Wed 2/12/25 Mon 3/3/25 Wed 3/19/25 Mon 4/7/25 Fri 4/11/25 Wed 4/30/25 Fri 5/16/25 Wed 6/4/25 Mon 6/23/25 Thu 7/10/25 **Fri 7/11/25** Thu 7/10/25 Fri 7/11/25

Mon 9/16/24 Mon 9/16/24 Mon 9/16/24

2025

Sep Oct NovDec JanFebMar AprMayJun Jul AugSep Oct

**Bldg A**

**Bldg B**

**Bldg C**

**Bldg D**

**Bldg E**

**Bldg A**

**Bldg B**

**Bldg C**

**Bldg D**

**Bldg E**

**Bldg F**

**Bldg G**

**Bldg H BldgJ**

**Bldg K Office**

**Bldg L**

**Bldg M**

**Bldg N**

**Bldg P**

**Bldg Q**

**7/10**

**CRW**

**9/16**

**9/16**

**9/16**

Project: KAANAPALI ROYAL - SLOPE

Date: Mon 8/12/24

Task Split Milestone Summary

Project Summary

External Tasks External Milestone Inactive Task Inactive Milestone Inactive Summary

Manual Task Duration-only

Manual Summary Rollup Manual Summary

Start-only

Finish-only Progress Deadline

Page 1

